APrIGF Multi-Stakeholder Steering Group (MSG) Meeting

24 Oct 2013 (Thu)

18:00 – 19:00 (UTC+8)

Room Office 1, Nusa Dua Convention Centre, Bali

Attendees(17):

Paul Wilson, APNIC  (Technical)

Pablo Hinojosa, APNIC  (Technical)

Jia-Rong Low, ICANN  (Technical)

Izumi Aizu, IHNS, Japan  (Civil Society)

Rajnesh Singh, ISOC  (Civil Society)

Cheryl Langdon Orr, ISOC AU, Australia  (Civil Society)

Gunela Astbrink, AuIGF, Australia  (Civil Society)

Masanobu Katoh, Japan  (Private Sector)

Younjung Park, KIGA, South Korea  (Civil Society)

Shreedeep Rayamajhi, ISOC Nepal  (Civil Society)

Hiro Hotta, JPRS, Japan  (Private Sector)

Maemura Akinori, JPNIC, Japan  (Technical)

Edmon Chung, DotAsia Organisation  (Technical)

Hong Xue, Beijing Normal University, China  (Academia)

Shahzad Ahmad, Bytes for All, Pakistan  (Civil Society)

Byoungil-Oh, Jinbonet, South Korea  (Civil Society)

Kilnam Chon, KAIST, South Korea  (Technical)

APrIGF Secretariat:

Yannis Li, DotAsia Organisation

Local Host of 2014:

Rajesh Chharia, ISPAI, India (Private Sector)

Neeraj Sonker, ISPAI, India (Private Sector)

Dr. Govind, NIXI, India (Government)

R.B. Marataham, NIXI, India (Private Sector)

Agenda:

- Election of 2nd Vice Chair

- Planning for APrIGF Hyderabad 2014

- Selection Process for 2015 Local Host

- A.O.B

Proceedings:

1. Election of 2nd Vice Chair

- Candidate nominated from the mailing list: 
Mr. Shahzad Ahmad, Bytes for All, Pakistan (Civil Society)

- With the number of candidates equal to the vacant seat, Shahzad was elected to be the 2nd Vice Chair of the MSG unanimously.

- The term will be effective immediately until 1 year from now.

2. Planning for APrIGF Hyderabad 2014

- The future APrIGFs are targeted to be organized at least 1 month ahead from the global IGF

- Current target dates: 1st week of August in 2014

- 4-Day Conference from Sat to Tue

- Day 0 will be the pre-event. Suggested topics: national initiatives

- Rajesh to check the venue NCC of Hyderabad and any clash with other major events at the target dates

- Action: A placeholder of the brief info about APrIGF 2014 should be posted on the main website

- Action: Rajesh to propose a theme & program to the mailing list as a starting point for discussion

- Government participation

- Dr. Govind will be responsible for outreaching to other government representatives

- YJ suggested to try reaching out to other inter-governmental organizations as well in addition to the ICANN GAC members

- Izumi suggested to invite non Asia Pacific Region government representatives as well

- It is suggested to promote remote participation among the government representatives as well due to the funding issue

- Private Sector Participation

- The participation from private sector is relatively lower than other stakeholder groups

- It is raised that there are many big IT companies with offices in India which the local host shall reach out to.

- Remote Participation

- It is suggested that remote moderators shall be allocated for each session

3. Selection Process for 2015 Host

- There is an intent of making the selection process of 2015 local host and the result announcement earlier than APrIGF 2014 with the below considerations:

- Providing longer preparation time for the future hosts

- Engaging the future host in the upcoming meeting

- Allowing newbies to bid for local host

- Target Announcement: APRICOT Bangkok Feb 2014 or Singapore ICANN Mar 2014
*WSIS deadline is 19th Feb which has to be avoided

- The RFP need to be revised and improved based on the experience from Seoul. The secretariat and KISA will work on the improvement and send to the mailing list for comment and to be discussed in the next meeting.

4. Recap & Reflections of IGF Bali

- Inter-regional Discussion

- Edmon reported that it is valuable to get together during the IGFs among the regional/national initiatives but there were in total 3 sessions of it, which was a bit too much since they were becoming repetitive in the content.

- Cheryl agreed and also suggested that a collaborative space is needed to make sure the AP voices is heard. She also raised that the survey shall be distribute even earlier

- It is generally positive to remain inter-regional dialogues at pre-events of IGF

- It is suggested that Labels /Tag of interests might be used for sessions with the recent development of IGF being organized based on languagues/culture & country such as Persian IGFs.

4. A.O.B

- There is a consensus on changing weekly MSG meetings back to monthly meetings

- Asia Pacific Hub of ICANN

- Jia-rong will share with the mailing list on a few slides that they have put together with the Matrix of activities

- Further discussion will be held in ICANN Buenos Aires

- Some activities is expected to be held in APRICOT Bangkok

The next meeting is scheduled to be on 29th Nov (Fri) 04:00-05:00am (UTC).