APrIGF Program Committee Meeting

11 Apr 2013 (Thu)

6:00 – 6:50 p.m. (UTC+8)

Function Room 6, Beijing International Hotel

ICANN 46 Beijing

Attendees(9):

Paul Wilson (Chair), APNIC

Izumi Aizu, Japan

Cheryl Langdon Orr, Australia

Minjung Park, KISA

Kenny Huang, TWNIC

Susan Chalmers, New Zealand

Adam Gosling, APNIC

Hong Xue, China

Duangthip Chomprang, ISOC

Secretariat(2):

Edmon Chung, DotAsia Organisation

Yannis Li, DotAsia Organisation

Agenda:

1. Call For Proposals

2. Operating Principles of MSG

3. Budget

4. Letter of Invitation

5. Bali IGF: linkages

6. AOB

Proceedings:

1. Call for Proposals

- RFP for 2014 Host:

- Secretariat to circulate the RFP and propose exact dates for applications

- Workshop Proposals for 2013 Seoul

- Consider suggesting a date for finalizing the proposals with confirmed speakers

- Secretariat to develop the framework for workshop submission based on the Global IGF one

2. Operating Principles of MSG

- Paul to send out a Final Call for Comment by April

3. Budget

- KISA/KIGA will send a revised Budget out to the Program Committee before next meeting which include the Government Fellowship

- ISOC shown interests in exploring to contribute to the Government Fellowship in attracting government participation

4. Letter of Invitation

- KISA will help with the official invitation to GAC members of ICANN

- Secretariat will draft a letter of invite on behalf of Program Committee to all other general parties

- It is agreed that a multiple rounds of invitation could be sent to different contact points of Government

5. Relationship with Global IGF

- Secretariat will reach out to the host of global IGF and invite them to the MSG as well

- Cheryl suggested to explore collaboration with APRALO of ICANN on regional strategy planning

- It is agreed that the activities in Bali is in scope of the PC which further discussion will be made next meeting

6. A.O.B.

- None

The next meeting is scheduled to be on 26th Apr (Fri) 04:00-05:30am (UTC).