APrIGF Program Committee Meeting

16 Aug 2013 (Fri)

04:00 – 05:00 a.m. (UTC)

WebEx Online Meeting

Attendees(11):

Paul Wilson, APNIC

Pablo Hinojosa, APNIC

Peng Hwa Ang, SIRC, Singapore

Cheryl Langdon Orr, Australia

Duangthip Chomprang, ISOC

Adam Peake, GLOCOM

Hong Xue, China

Asif Kabani, Pakistan

Keith Davidson, Internet NZ

Rajesh Chharia, ISPAI

Save Vocea, ICANN

Local Host & Secretariat(5):

Dongman Lee, KIGA

Younjung Park, KIGA

Kye-nam Lee, KRNIC

Dong-eun Won, KISA

Seo Yun Jin, Event Company

APrIGF Secretariat(2):

Yannis Li, DotAsia Organisation

Edmon Chung, DotAsia Organisation

Apologies(4):

Rajnesh D. Singh, ISOC

Kuo Wei Wu, ICANN

Susan Chalmers, Internet NZ

Kenny Huang, APNIC

Agenda:

- Review & Follow up from Last Meeting

- Program Review & Follow Up

- Updates from Local Host

- APrIGF 2014 Local Host

- A.O.B

Proceedings:

1. Review & Follow up from Last Meeting

- The minutes is reviewed and adopted

2. Program Review & Follow Up

- The volunteer team Asif, Susan, KIGA and the Secretariat has drafted the below Orientation Session:

1. Scene setting (15 min) [Paul Wilson, Chair of MSG, TBC]

1.1 What is the IGF? (Mandate and Background)

1.2 What is multi-stakeholder model of Internet Governance?

1.3 What are the different themes and current issues respectively the IGF

2.  About APrIGF & YIGF (15-20 Minutes) [Edmon, DotAsia]

2.1 History, Development & Current Status

2.2 How it relates to the global IGF and national IGFs

3.  Overview of the programme of APrIGF 2013 Seoul (~10mins) [Prof. Jae Choen Park, KIGA]

3.1 Explain the different streams and Themes

4. Q&A

5. Final Announcements and Reminders / Wrap up

5.1 Subscribe to discuss@aprigf.asia

- Comments & Suggested Changes:

- Dongman suggested that Prof. Park would be more suitable to speak about local Internet governance situation instead of the program overview since he is not much involved in the beginning of the planning process while Dongman himself or Prof. YoungEum Lee would be a better person to speak about Part 3. The comment is agreed by the PC

- Duangthip suggested to add a slot to explain different major Internet organizations, e.g. ICANN, APNIC, ISOC, etc. The suggestion is agreed by the PC.

- Updates on Status of different workshop by the secretariat which most of the workshop are already finalized. Special attention has been made to some sessions due to the pending list of speakers

- Workshop on ISOC Chapters was yet to be finalized. Duangthip and Edmon agreed to help out to reach YJ Park (Workshop Organizer) to offer support. Targeted to get the updated proposal by next meeting

- Workshop #13 Cyber Security was yet to received response from the workshop organizer. Local secretariat KISA is helping to get an update by next meeting.

- Hong asked about whether the proposal about Child Online Safety from CNNIC is still there. The secretariat explained that it has been merged with Proposal #32 Governance for Better internet for Kids. Asif voiced out that he would like to participate in the panel.

- Summary Sessions: yet to be structuralized. Secretariat will initiate with Asif, Gunela, Duangthip and Edmon after the meeting to coordinate in email.

- Edmon suggested that the PC also to actively look into the current panels of different workshop and help with suggesting additional speakers to ensure the multi-stakeholderism. For example some of the sessions’ panels only involved stakeholders from one organization such as the ICANN workshop. While Hong clarified that the session was means to be a dialogue with all the floor participants and the 4 panel speakers are all moderators. Paul suggested Edmon to take the lead to send out a list of suggestions after the meeting.

3. Update from Local Host

- Website constantly updating with the new information from workshop organizers.

- Final confirming with the local facilities

4. APrIGF 2014 Local Host

- Only 1 proposal received within deadline which is from ISPAI & NIXI of India.

- PC will take at look at the proposal and discuss in the next meeting

- Adam raised out that the secretariat should make sure there is enough quorum for next meeting if a voting is required. Paul suggested Adam to look into what exactly have to be done

4. A.O.B

- KISA suggested having a face-to-face meeting next Friday since many of the PC members might be in Xi’an for the APTLD and APNIC meeting. Yet the PC decided to just keep the call meeting at the same time.

The next meeting is scheduled to be on 23rd Aug (Fri) 04:00-05:00am (UTC).